## Summary
LMNS Equity and Equality Action Plan: Derbyshire LMNS
Vision | To reduce the avoidable and unjust differences in pregnancy outcomes for the population of Derby and Derbyshire
Aims and values | · equity for mothers and babies from Black, Asian and Mixed ethnic groups and those living in the most deprived areas · equity and race equality for staff.
Our local community | In Derby City, 1 in every 3 births were to women and birthing people from a Black, Asian and mixed ethnicity during 2020/21 compared to the England average of 1 in every 5 births. For women and birthing people in Derbyshire County this was 1 in 20 births In Derby City 24 areas (15.9%) are in the most deprived nationally. For Derbyshire County this is 22 areas (4%).
Ambitions (Three year plan) | • To reduce inequalities for all in access, experience, and outcomes. • Targeted support where health inequalities exist in line with the principles of proportionate universalism. • Services listen to and work with women from all backgrounds to improve access, plan, and deliver personalised care. DMNV ensures all groups are heard, including those most at risk of experiencing health inequalities. • The NHS collaborates with local authority services, other public sector organisations, and a wide range of private and voluntary sector organisations to address the social determinants of health, which are a significant driver of health inequalities.
Priorities | • Priority 1: Restore NHS services inclusively • Priority 2: Mitigate against digital exclusion • Priority 3: Ensure datasets are complete and timely • Priority 4: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes • Priority 5: Strengthen leadership and accountability.
How progress will be measured nationally | Perinatal mortality metrics Indicator: The stillbirth and neonatal mortality rate per 1000 births for Black and Asian babies divided by the rate for Whilt babies in the UK expressed as a ratio. (Source MBRRACE-UK) Baseline NHS Long Term Plan 1.7 (2017) Indicator: The modelled difference in the stillbrith and neonatal mortality rate per 1000 births between the most and least deprived communities in England, measured using the slope index of inequality. (Source ONS) Baseline NHS Long Term Plan 4.39 (2017) The English maternal morbidity outcome indicator (EMMOI) Assesses the rates of various pregnancy complications and can, in contrast to investigation of maternal deaths, be compared across regions or LMNS.

## Priority 1
Priority 1 - Restore NHS service inclusively
At national level, the decline in access among some groups during the first wave of the pandemic broadly recovered in later months. Some pre-existing disparities in access, experience and outcomes have widened during the pandemic. 56% of the pregnant women admitted into hospital with Covid 19 were from ethnic minority groups.
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Continue to implement the COVID 19 four actions: | Increase support for at risk pregnant women | Clinicians to have a lower threshold to review, admit and consider multidisciplinary escalation in women from ethnic minority groups | Perinatal Quality and Safety Group |  | DoM - CRH & UHDB | Ongoing | Trusts can evidence that a policy is in place and demonstrate how often this has been used. | Delivered, not yet evidenced | Complete | CRH - Policy around matenity care included informaion on lower threshold of care UHDB - Guideline in place to support lower threshold to review, admit and consider escalation in women from ethnic minority groups. (Guideline: Covid-19 infection in Maternity: Personalised assessment and management of Covid-19 risk factors (including ethnic risk factors); vaccination; inpatient and outpatient care)
|  | Reach out and reassure pregnant women from BAME groups, those with protected characteristics and those living in the most deprived areas with tailored communications | UHDB: Translate patient information leaflets into the top 5 spoken languages | Operational Delivery Group |  | UHDB Lead CoC Midwife | 2023-03-01 | UHDB CoC lead midwife to provide copies of the patient leaflets and to provide a report on patient feedback at the ODG | Delivered, not yet evidenced | On track | CRH electronic records will appear in the chosen language set on their internet browser language settings. Will be able to read the links to get the information leaflets in their chosen language. Action to aviod digital exclusion - To review top 5 languages and ensure leaflets given out by the Trust are available UHDB - Translation available on trust webiste and Healthzone app. All patient information leaflets have been translated into the top 5 languages for UHDB and require distribution on all platforms. Also gap analysis of national documents used for patients have been translated if not available in local top spoken languages or provider will translate).
|  |  | Develop information videos for the Deaf community around what to expect from Derbyshire maternity services | Operational Delivery Group |  | DMNV | 2023-03-01 | DMNV provide a copy of the video and patient feedback at the ODG | Not yet delivered | Not started
|  |  | To undertake a engagement mapping exercise and identify any particular population groups that are not currently being engaging with | Equity and Equality Core Group |  | ICB Engagement lead | 2023-09-01 | ICB engagement lead to present to the Equity and Equaltiy group a list of those population groups that have been engaged with, a list of those that are missing and identify ways to engage in the future as evidenced in minutes and action logs | Not yet delivered | On track
|  |  | To undertake a patient experience survey to gather further insight from BAME groups, those with protected characteristics and those living in deprived areas around maternity services | Equity and Equality Core Group |  | ICB Patient experience team | 2023-06-01 | Patient experience team to provide a report on survey results, response rate by demographics, themes identified and actions identified to be presented at the Equity and Equaltiy Improved and diverse range of service users' experience to enhance maternity services. Local evidence of working with women and famiiles to improve services including co-production. | Not yet delivered | On track
|  | Trusts to discuss vitamin supplements and nutrition in pregnancy with all women | Understand the uptake of Healthy Start and any inequalities around this | Maternal Health and Wellbeing |  | Public Health | 2024-03-01 | Report on the percentage take up of Healthy Start with a focus on areas of deprivation with an action plan to improve up take twice yearly at the HWG and ODG | Not yet delivered | On track | This is an action in the Infant feeding Strategy - data is becoming available
|  |  | Implementation of the Vitamin D pathway during pregnancy - POIROD (Pregnancy Outcome Inequality Reduction by Optimising Vitamin D) | Operational Delivery Group |  | UHDB Audit Midwife | 2023-09-01 | Work presented and discussed at ODG which provides evidence of a pathway and the uptake and effectiveness along with further actions required | Delivered, not yet evidenced | On track | UHDB - in place - need to get data. CRH implemented the pathway but not sure if they have any data
|  | Trusts to record data on maternity information systems on the ethnicity of every woman, as well as other risk factors, such as living in a deprived area (postcode), co-morbidities, BMI, and aged 35 years or over to identify those most at risk of poor outcomes. | Monitor data quality on ethnicity and risk factors. Identify if any improvements are need in data collection | Workforce and data planning |  | UHDB & CRH Digital Midwives | 2024-03-01 | Trusts to provide a report on the percentage of records that provide ethnicity risk factors such as living in a deprived areas, co-morbidities, BMI and age groups quarterly to the workforce and data planning group and ODG. | Delivered, not yet evidenced | On track | CRH current electronic system collects this data and is available on the maternity data set (MSDS). Also looking at including gender onto CRH PAS system and electronic maternity records (work in progress) captured on perinatal scorecord UHDB Data entry can be reviewed, although known inability of system to extract data - different EPR systems collect postcode and BMI. Ethnicity is routinely recorded on the Trust electronic systems and is available in the MSDS. Other items such as postcode is also available and routinely collected. The data quality for both of these is very high. BMI is collected at booking and data quality across the Trust is around 93% in general and there are sections set up specifically in the booking forms on both Lorenzo and Meditech to collect Risk Factors. All the data is extracted and is available in the MSDS.

## Priority 2
Priority 2 - Mitigate against digital exclusion
The NHS Long Term Plan asks integrated care systems (ICS) to implement PCSPs in maternity services. This tool supports and documents the conversations and decision-making process from which an agreed plan is developed that reflects an holistic assessment of the woman’s health and wellbeing needs. The PCSP should set out a woman’s decisions about the care and support she wants. Women need evidenced-based information in advance of decision-making so that they are well prepared
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Ensure personalised care and support plans (PCSPs) are available in a range of languages and formats, including hard copy PCSPs for those experiencing digital exclusion | 90% of midwives, MSWs and obstetricians to receive training in personalised care | All current maternity staff to be made aware of the Personalised Care Institute training and PCSP via training at CRH or access to the UHDB PCSP video and QR code by March 2023 New starters to the Trust to be signposted to the above A survey to be completed by staff to audit any improvement in knowledge of PCSP | Choice and Personalisation |  | CRH & UHDB PCSP champions LMNS Lead Midwife for Quality and Safety | 2023-03-01 | The number of women with a Personalised Care and Support Plan which covers: - antenatal care by 17 weeks gestation - intrapartum care and postnatal care by 36 weeks gestation The numbers of women who have all of the above in place by the gestational dates All indicators are available with breakdowns by ethnicity and index of multiple deprivation Feedback on personalised care gathered by DMNV from a wide range of service users | Not yet delivered | On track | UHDB - Training has been provided on mandatory training days, through a video at UHDB available to staff and by adding the PCI training to staff training passports
|  | Personalised care and support plans (PCSPs) are available in a range of languages | PCSP is translated into top 10 language for Derbyshire Translated version to be made accessible through both Trust websites and UHDB Healthzone app | Choice and Personalisation |  | LMNS Lead Midwife for Quality and Safety | 2022-12-01 |  | Delivered, not yet evidenced | On track | CRH - Available on the Health Zone app which is translatable and in a paper version for digital exclusion. Translated versions saved to shared drives for staff to access as required
|  | Develop an easy read suitable for pregnant people with lower literacy skills | Current PSCP to use less words and more images for ease of access Use feedback from HMP Foston to ensure the content is suitable for those from disadvantaged groups Easy read version to be made available from community midwives and at HMP Foston | Choice and Personalisation |  | LMNS Lead Midwife for Quality and Safety Birth companions | 2023-06-01 |  | Not yet delivered | Not started
|  | PCSP to be available and used by 100% of service users | All service users will be able to access and use a PCSP in a format suitable for them. Choice will be given and accommodated by all staff | Choice and Personalisation |  | CRH & UHDB Midwives and medical staff | 2023-03-01 |  | Not yet delivered | On track | PCSP is offered to all women at UHDB in Hand held records. Translated versions available on request (printable). CRH offer all women My Pregnancy Notes digitally and have a paper version and translated version for printing on request
|  |  | Data will be collected from the IT systems and through Friends and Family Test survey responses | Choice and Personalisation |  | CRH & UHDB Midwives and medical staff | 2023-06-01 |  | Not yet delivered | Off track | Both providers are developing the FFT to include informed decision making questions and reviewing the process for receiving this information. UHDB - Offer by 17wks - QHB 90%,RDH 51% Offer by 36wks - QHB 88%, RDH 6.5%

## Priority 3
Priority 3: Ensure datasets are complete and timely
Systems are asked to continue to improve the collection and recording of ethnicity data.
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Maternity information systems continuously improve the data quality of ethnic coding and the mothers postcode, recording, collating, analysing, reporting and interpretation | Valid postcode for mothers at booking in 95% of women booked in the month. Valid ethinc category for at least 80% of the women booked in the month | Recording of ethnicity and postcode data at booking Ongoing audit of compliance Identify any actions required | Perinatal Safety Forum |  | CRH/UHDB Digital Midwives | 2023-12-01 | Report is presented twice yearly at the PSF and PQSG on compliance against: - Data submitted to Maternity Services Data Set (MSDS) contains valid postcode for mother at booking in 95% of women booked in the month - Data submitted to MSDS includes a valid ethnic category for at least 80% of the women booked in the month. This is minuted in meetings and actions for improvements logged | Delivered, not yet evidenced | On track | CRH: CNST submission Feb 23 - compliant with data collection in Safety Action 2 UHDB: CNST submission Feb 23 - compliant with data collection in Safety Action 2
|  | Data gaps and actions to address identified (e.g. alcohol use in early pregnancy, BMI at booking, perinatal mental health & smoking) | Identification of any data gaps Develop action plan to improve | Perinatal Safety Forum |  | CRH/UHDB Digital Midwives | Ongoing | Report presented at PSF & PQSG twice yearly on any data gaps with an associated action plan to address. | Not yet delivered | Not started | UHDB - System issues with data postcode and clinical data
|  | Implement an LMNS Health Inequalities Dashboard | Liaise with Birmingham Womens and Childrens Hospital to understand the scope Understand the CSU data reporting cycle | Perinatal Quality and Safety Group |  | ICB BI team LMNS CRH Digital Midwives UHDB Digital Midwives | 2025-03-01 | A LMNS dashboard is developed and areas of inequality in relation to maternity and neonatal services are identified with action plan developed to address. | Not yet delivered | Not started
2 | Review neonatal datasets to ensure that relevant information on postcode and ethnicity is recorded in all records | Investigate if neonatal datasets can be analysed to understand if there are groups overrepresented and any factors or learning | Public Health to identify if there is resources to undertake an analysis of neonatal data | Neonatal Working Group |  | Neonatologists Public Health | 2024-03-01 | Report to the Neonatal group and ODG twice yearly with the percentage of neonatal records that have ethnicity and postcode recorded and any actions required for improvement. | Not yet delivered | Not started

## Priority 4a
Priority 4: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes
4a: Understand your population and co-produce interventions
The Maternity Transformation Programme is one of the preventative programmes that are engaging those at greatest risk of poor health outcomes
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery progress | Progress status | Update May 23
1 | Understand the local populations maternal and perinatal health needs (including the social determinants of health) | The commitment to a programme of health needs analysis with a review of findings and co-produced actions/recommendations | Undertake a maternal alcohol needs assessment | Maternal Health and Wellbeing |  | Public Health - County leading | 2023-06-01 | Work presented and discussed at HWB subgoups (documented in minutes). Actions have been developed by members of the HWB group to respond to the information (documented in minutes or via a report) Local evidence of working with women and families to improve services | Not yet delivered | On track | Findings to be presented at ODG in June 23.
|  |  | Understand the local maternal healthy weight pathway and identify any inequalities | Maternal Health and Wellbeing |  | Public Health | 2024-03-01 |  | Not yet delivered | On track | Work has started. Andy White (City PH) and Jo MCGarrigle (County PH) leading on this
|  |  | To influence the JSNA to ensure that maternity and neonatal areas are considered to better understand this popuation group, idenitify needs and inequalities. in line with work around Start Well. | Maternal Health and Wellbeing |  | LMNS Public Health | 2024-03-01 |  | Not yet delivered | Not started | This will support work on Start Well one of the priorities for the ICS
2 | Map the community assets which help address the social determinants of health | Understand the current community assets in place | Undertake and refresh the work undertaken in 2021 to identify available community directories & promotion of existing resources such as children's service directory in the County and Derby and Derbyshire Health and Wellbeing website | Equity and Equality Core Group |  | Public Health | 2024-03-31 | A review of referal to service and attendance over time in undertaken and presented at the Equity and Equality Core Group. A review of effectiveness and cost effectiveness of digital interventions is shared at ODG and evidenced in the minutes Local evidence of working with women and families to improve services | Not yet delivered | Not started | Available directories were identified and summarised in the E&E analysis in 2021. There are many complexities as not all up to date, searchable in different ways, not all complete. Given the changes to undertake a refresh during 2023/24
|  |  | Undertake scoping exercise to understand any added value of bringing MotherHub website back online. | Maternal Health and Wellbeing |  | Public Health/ Derby City Council/LMNS PMO | 2024-03-01 |  | Not yet delivered | Not started | MotherHub was a website that was CCG owned and managed. This was hacked and so no longer active. Need to have discussions regarding the added value of having this brought back online. This scoping needs to be alongside work in City and County to deliver the Start for Life/ Family Hubs guidance on publishing the offer, specifically linking to the Family Hubs work in the City.
3 | Understand the staff experience using Workforce Equality Scheme (WRES) data | See Priority 4d
4 | Use this understanding of local maternal and perinatal health needs (including social determinants of health) to deliver evidence based interventions to improve equity for women and babies and race equality for staff | Set out a plan to co-produce interventions to improve equity for mothers, babies and race equality for staff | Identify areas that require co-production Work with ICB Engagement Team to support volunteers to be involved in co-production | Equity and Equality Core Group |  | ICB engagement lead DMNV LMNS | Ongoing | Report produced and presented at the Equity and Equality Group and ODG that outlines the plan for co-production in maternity and neonatal services and the number of volunteers involved in co-production Local evidence of working with women and families to improve services, including co-production | Not yet delivered | On track

## Priority 4b
Priority 4: Accelerate preventative programmes tha engage those at greatest risk of poor health outcomes
4b: Action on maternal mortality, morbidity and experience
LMNSs are asked to ensure equity in access, experience and health outcomes for women from Black, Asian and Mixed ethnic groups and those women living in the most deprived areas. They may consider other protected characteristics and inclusion groups.
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery progress | Progress status | Update May 23
1 | Implement maternal medicine networks to help achieve equity | Trusts to align to a maternity medicine network and implementation of speciality pathways | Confirmation of alignment for CRH recognising patient flows into Yorkshrie & Humber All pregnant people with medical problems have access to specialist advice and care. | Perinatal Quality and Safety Group |  | CRH UHDB LMNS | 2023-03-01 | Trusts to provide a quarterly report on the number of referrals made to the MMN by each Trust on a quarterly basis broken down by level of deprivation of the mother’s postcode and ethnicity to the PQSG. | Delivered, not yet evidenced | On track
2 | Offer referral to the NHS Diabetes Prevention Programme to women with a past diagnosis of gestational diabetes mellitus (GDM) who are not currently pregnant and do not currently have diabetes | Where a woman is diagnosed with GDM, maternity service to inform GP practice. Women with a history of GDM should be reviewed and offered testing for diabetes postnatally and subsequent annual checks (with a glycaemic test) by their GP practice as described in the NICE guideline [NG3] diabetes in pregnancy. Women with a past diagnosis of GDM who are not currently pregnant should be offered a referral to the NHS Diabetes Prevention Programme once a blood test has excluded Type 2 diabetes. | Pilot a gestational diabetes pathway in Derbyshire at UHDB Roll out in Chesterfield Maintain as Business and Usual | Operational Delivery Group |  | Diabetes Delivery Group CRH & UHDB Diabetes Midwives PCNs and GPs | 2023-12-01 | Report presented that outlines the percentage of people with previous GDM who are offered a referral (by demographic group, age group, gender, ethnic group, deprivation) on a quarterly basis. Evalutation of pilot work presented and discussed at ODG with actions and recommendations documented in minutes. | Not yet delivered | On track | March 23 - Pilot pathway in place (UHDB) and on DDICB intranet https://intranet.ddicb-nhs.uk/download/development-of-gestational-diabetes-pathway-in-derbyshire/. There are two GDM tailored remote groups running. Next steps to monitor and review the process and uptake as part of assurance process. Roll out to Chesterfield
3 | Implement NICE CG110 antenatal care for pregnant women with complex social factors. | Improved access to antenatal care and outcomes for pregnant people with complex social factors (particularly alcohol or drug misuse, recant migrant or asylum seeker status, difficulty reading or speaking English, aged under 20, domestic abuse) | Each Trust to benchmark against the NICE guidance Establish data extraction Monitor the number of women who attend for booking at 10, 12+6 and 20 weeks and those who attend for the recommended number of antenatal appointments, in line with their pathway. | Operational Delivery Group |  | CRH & UHDB Maternity Governance Teams | 2024-03-01 | Agreed definition of 'complex social factors' across LMNS and wider system. Trust level assurance that meeting NICE CG110 with ability to present data on the percentage of pregnant people with complex social factors by demographic group that: - attend booking by 10 weeks, 12+6 weeks and 20 weeks - attend for the recommended number of antenatal appointments in line with national guidance - experience, or have babies who experience, mortality or significant morbidity - the number of appointments each woman attends -the number of scheduled appointments each woman does not attend - satisfaction with services recorded and monitored | Not yet delivered | On track | CRH: Data extraction already takes place via MSDS. All data is collected at booking. All consultations then continue to produce data that continues to provide data. Information should be able to be pulled and corolated. Missing data is monitored by auditing 10% of records each month. UHDB - All data is captured but need to ascertain if current digital system can support this. Likely this will require a manual audit to follow an individual along their pregnancy pathway, digital system will pull out overall data not the same cases. All the data is captured in the Trust electronic systems and extracted and whilst processes are in place to measure the booking information digitally, there are not currently any in place to measure whether there are the correct number of attendances within a given pathway. The data is however flowing into the MSDS but this is likely to require a manual audit to evidence. DNA'd contacts in the community are not recorded on Lorenzo/Meditech in a way that can be audited, it is entered by freetext. Outpatient appointment DNA's can be audited.
|  |  | To explore how Midwifery Support Workers linked to Continuity or Carer teams can support pregnant people with complex socila factors with health and wellbeing by upskilling to offer very brief advice, signposting and support | Operational Delivery Group |  | CoC Lead Midwives | 2024-03-01 | The providers to survey women with complex social factors to inlcude response rate and satisfaction with the service and present to ODG twice yearly. | Not yet delivered | Not started
4 | Implement maternal mental health services with a focus on equity of access and addressing unmet need | Understanding activity of the new MMHS and to undertake an evaluation which will include understanding the women's postcode and ethnicity and how the service is reaching out to women from ethnic backgrounds nd deprived areas | Patient information that is accessible and reflects the needs of Black African, Asian and White other ethnic groups; those living in the most deprived areas Equitable access and service user expreience and outcomes for Black African, Asian and White other ethnic groups; those living in the most deprived areas | Operational Delivery Group |  | MMHS Project Manager, Derbyshire Helathcare Trust | 2023-09-01 | Data and evaluation report presented to ODG and LMNS Board with recommendations /actions discussed and recorded in minutes. | Not yet delivered | At risk | No update regarding evaluation of MMHS UHDB - An indication of volume is required to assess risk, historical data cannot be used due to issues with consent, so data will be captured moving forward and anonymised. This will need to include postcode and ethnicity.Development of resources which reflect a variety of cultures so is accessible and meets the needs of the local population. Does access into services reflect the demographics of the population.NHS data opt out - The NHS Data Opt Out is collected nationally, it is the role of local trusts to check against the national list. Each trust will have its own procedure for checking this. If you want to separately allow patients to decline for this project the method and storage of that decision would need to be done separately
5 | Ensure personalised care and support plans are available to everyone | See Priority 2
6 | Ensure the MVP reflects the ethnic diversity of the local population, in line with NICE QS167 | To continue to engage with and support women of ethnic diversity and the most deprived to encourage their membership within the DNNV to reflect the local population. | The committee membership and engagement reported annually at the AGM will include representatives from the community to reflect diversity. | Operational Delivery Group |  | DMNV Chair | 2023-04-01 | Percentage of patient members of DMNV who are from ethnic minority groups and from the most deprived areas Documented engagement activity by organisation, area of interest, community of focus shared at ODG annually | Not yet delivered | On track
|  |  | Events to promote engagement with local faith groups and support groups aimed at ethnically diverse communities will be included in the workplan for DMNV |  |  |  | Ongoing |  | Not yet delivered | On track
|  |  | Face to face meetings will be held across Derbyshire in different communities and settings to publicise DMNV’s role. |  |  |  | Ongoing |  | Not yet delivered | On track
|  |  | Promotional material will be placed in appropriate locations to encourage attendance from ethnically diverse communities |  |  |  | Ongoing |  | Not yet delivered | Not started

## Priority 4c
Priority 4: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes
4c: Action on perinatal mortality and morbidity
LMNS are asked to address the leading causes of perinatal mortality and morbidity for babies from Black, Asian and Mixed ethnic groups and born to women living in the most deprived areas. LMS may consider other protected characteristics and inclusion groups.
Intervention | Action | Detail | Milestones | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Implement targeted and enhanced continuity of carer, as set out in the NHS Long Term Plan. | This means that, as continuity of carer is rolled out to most women, women from Black, Asian and Mixed ethnic groups and women living in deprived areas are prioritised, with 75% of women in these groups receiving continuity of carer by 2024. It also means ensuring that additional midwifery time is available to support women from the most deprived areas. | Both Trusts have an action plan in place to implement targeted and enhanced continuity of carer. | Choice and Personalisation |  | MCoC leads |  | Trusts to provide a written report on the percentage of people on CoC pathway by demographic group (age group, ethnic group, deprivation) to ODG twice yearly. Placement on a Continuity of Carer pathway of Black, Asian and Mixed ethnic groups and those living in the most deprived areas - Maternity Services data Set | Not yet delivered | At risk | Mar 23 -Three CoC teams are in place: 2 at UHDB and 1 at CRH. UHDB has been successful in securing Enhanced Midwifery Continuity of Carer (MCoC) funding in 2022/23 specifically for teams working in the 10% most deprived neighbourhoods. CRH will be considered for the next round of funding for the team which will be going live in Q3 23/24.
2 | implement a smoke-free pregnancy pathway for mothers and their partners. | NHS Tobacco Dependency pathways available to 46% of maternal smokers by March 23, increasing to 100% by March 2024 May 23: 57.5% in March 23. Only just started to received figures | All midwives and maternity support workers will attend a Saving Babies Lives training day which includes CO monitoring and very brief advice (VBA) | Maternal Health and Wellbeing |  | CRH & UHDB Tobacco Champion Midwives LMNS Lead Midwife for Quality and Safety | Ongoing with annual review to meet 90% compliance | Element 1 of SBLv2 compliance and a decrease in smoking at booking and delivery May 23 - CRH has 100% compliance of element 1 of SBLv2 Audits through the IT systems and manual to provide a monthly trajectory and update at the HWB group | Delivered, not yet evidenced | Complete | Annual mandatory training day
|  |  | All medical staff will receive training on VBA | Maternal Health and Wellbeing |  |  | Ongoing with annual review to meet 90% compliance |  | Not yet delivered | On track | Plan in place to target all medical staff and trainees
|  |  | All antenatal appointments will include CO monitoring | Maternal Health and Wellbeing |  |  | 2023-01-01 |  | Delivered, not yet evidenced | On track | Currently promoted to offer at every visit however NICE guidance now changed to reflect only booking and 36 week offer
|  |  | All pregnant smokers will be seen by inhouse tobacco dependency advisors and offered NRT | Maternal Health and Wellbeing |  |  | 2023-01-01 |  | Delivered, not yet evidenced | On track | Maternity specific advisors in place at both Trusts
|  |  | All pregnant smokers admitted as an inpatient will be given VBA, NRT and referred to advisors if not already on the pathway | Maternal Health and Wellbeing |  |  | 2023-01-01 |  | Not yet delivered | At risk | NRT available on the wards. CRH offer NRT on admission. UHDB to improve staff knowledge of pathway and promote use of NRT
|  |  | All partners of pregnant smokers and new parents who smoke will be offered tobacco dependency support | Maternal Health and Wellbeing |  |  | 2023-09-01 |  | Not yet delivered | On track | Discussions with 0-19's regarding offering support postnatally. Referral pathway shared to ensure referral is offered. Health visitirs to receive training in VBA and intensive health visiting service to receive training in CO monitoring. CRH to offer partners CO and TD support at 12 week dating scan appointment
|  |  | NEW May 23 Derby/Derbsyhire Smoking in Pregnancy Group to develop further understanding of inequalities in smoking prevalence among pregnant women in Derby and Derbyshire to create intelligence to enable the co-production of services and targeted interventions and resources | Maternal Health and Wellbeing |  |  | 2024-03-01 |  | Not yet delivered | Not started
|  |  | NEW May 23 Learn from the UHDB pilot for NRT to be available and VBA offered in community where there is an interpreter to attend a city antenatal clinic with high proportion of Eastern European smokers | Maternal Health and Wellbeing |  |  | 2024-03-01 |  | Not yet delivered | Not started
|  | Reduce smoking in pregnancy to less than 6% as per target that was set in the Tobacco Control Plan 2017. | Further develop the in house tobacco dependency pathway to include rereferral, support for partners and postnatal support | Maternal Health and Wellbeing |  | LMNS Lead Midwife for Quality and Safety | 2025-03-01 |  | Not yet delivered | Not started | Discussions with 0-19's service and LA offer. Midwives to be made awrae of referral pathway to LA. Not currently able to offer support for partners or postnatal support until TDA numbers increase
|  |  | Explore funding for incentive schemes to encourage compliance with the programme. | Maternal Health and Wellbeing |  |  | 2025-03-01 |  | Not yet delivered | Not started | National funding to be made available to support incentives for pregnant smokers. Awaiting guidance. As a system we will need a single policy around vapes - this sits with Public Health colleagues.
|  |  | Monitoring of pregnancy outcomes to determine whether the pathway has been successful in reducing perinatal mortality and morbidity | Maternal Health and Wellbeing |  |  | 2025-03-01 |  | Not yet delivered | Not started | Smoking status is recorded for all perinatal mortality cases. Champion midwives to be involved in revieing of these cases
3 | Implement an LMS breastfeeding strategy and continuously improve breastfeeding rates for women living in the most deprived areas. | Implement the Infant Feeding Strategy ensuring that actions are continuously co-produced | Development and refinement of milestones needed to focus efforts 'on continuously improve breastfeeding rates for women living in the most deprived areas.' | Maternal Health and Wellbeing |  | Public Health | Ongoing | Evidence of achievement of baby friendly accreditation | Delivered, not yet evidenced | On track | Infant Feeding Strategy completed Feb 23.
|  |  | Increase GPs confidence in supporting breastfeeding agenda through training | Maternal Health and Wellbeing |  | Public Health | 2024-03-01 |  | Not yet delivered | On track | Work has started made significant progress. County Public Health leading T&F group, supported by infant Feeding Specialists and Health Education Derbyshire. PH budget identified to support development of training resources.
|  |  | Develop an understanding of inequalities to support services to co-produce and target interventions in areas of lower prevalence | Maternal Health and Wellbeing |  | Public Health | On-going |  | Not yet delivered | On track | This has started. County and City PH have data analysis/ dashboards shared with infant feeding steering group to support services in targeting support based on understanding of inequalities. This is an ongoing action.
|  |  | Neonatal services to achieve accreditation and other services to maintain UNICEF BFI accreditations | Maternal Health and Wellbeing |  | CRH & UHDB Public Health LMNS | On-going |  | Not yet delivered | On track | This will be an ongoing action for the Infant Feeding Steering Group. CRH NNU have certificate of commitment for BFI however funding is required for staff to progress with this
4 | Provide culturally-sensitive genetics services for consanguineous couples. | Improving access to culturally-sensitive genetics counselling can empower affected families and reduce unexpected affected births | Identify if and what the offer is in place at both Trusts | Operational Delivery Group |  | CRH & UHDB | 2023-06-01 | Trusts to provide numbers and percentage of people referred to genetics counselling twice yearly at the PQSG | Not yet delivered | On track | CRH - if disclosed referral to clinical genetics in Sheffield . Need to ensure clinicians confident to have the conversation UHDB - The Fetal and Maternal Medicine Department refer to clinical genetics in Nottingham or Birmingham (postcode dependant) for a variety of reasons, this may be during the pregnancy if anomalies are found on scan or diagnostics testing, or referral may be pre pregnancy or post pregnancy loss.
|  | Shared understanding of local risks impacting perinatal mortality and morbidity | Identifying themes and shared learnings through discussions with Specialist Midwives, Obstetricians, Neonatologists, Public Health, Patient Safety teams | Perinatal Quality and Safety Group |  | PMRT | Ongoing |  | Not yet delivered | On track

## Priority 4d
Priority 4: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes
4d: Support for maternity and neonatal staff
LMNS are asked to equip maternity and neonatal staff to provide culturally competent care and ensure that maternity and neonatal staff experience race equality in the workplace
Intervention | Action | Detail | Milestone | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Roll out multidisciplinary training about cultural competence in maternity and neonatal services. | To include cultural competence training in PROMPT training days for midwives and neonatal staff | All maternity and neonatal staff to have received cultural competency training | Workforce, digital and data planning |  | CRH & UHDB Midwifery Practice Development Teams | Ongoing | Report on the percentage of maternity and neonatal staff who attended training about cultural competence in the last two years to be presented at the Workforce, digital and data planning group and ODG. | Not yet delivered | On track | CRH - 22 Staff attended a baby lifeline Cultural completency training April 2023 UHDB commenced in Jan 2023. Cultural competency training to be undertake by MDT in June 2023.
|  | To measure how effectively maternity services foster diversity and inclusion identifying areas in which further work is required. | To undertake a baseline survey of maternity and neonatal staff exploring 4 key areas: perceptions of inclusion and respect; a workplace free from discrimination, fair and equal access to opportunities and leadership commitment to diversity values To conduct focus groups and face to face interviews to triangulate the results from the survey | Workforce, digital and data planning |  | CRH & UHDB CoC Midwives IPiP Head of Maternity Transformation Programme | 2023-06-01 | Report on the survey completion including response rate and how representative the survey has been, themes identified with an action plan developed | Not yet delivered | On track
2 | When investigating serious incidents, consider the impact of culture, ethnicity and language. | Ensure ethnicity and language is recorded in all serious incidents and that these are considered when investigating serious incidents | Analysis of serious incidents and themes identified in relation to culture, ethnicity and language with identified actions | Perinatal Quality and Safety Group |  | CRH & UHDB Governance Midwives |  | Quarterly reports on the percentage of maternity and neonatal serious incidents relating to patient care with a valid ethnicity code and percentage of PMRT cases with a valid ethnic code. | Not yet delivered | On track | Regional team has undertaken analysis and shared with Trusts UHDB invited in if limited English/translation cards. Themes how are they captured and leasons learned.
3 | Implement the Workforce Race Equality Standard (WRES) in maternity and neonatal services and understand the staff experience using Workforce Equality Scheme (WRES) data | Implementing the Workforce Race Equality Standard (WRES) is a requirement for NHS commissioners and NHS healthcare providers including independent organisations, through the NHS standard contract. | Conduct a baseline assessment of the experience of maternity and neonatal staff by ethnicity using WRES indicators 1 to 8. To interrogate the WRES data for each Trust and identify a more accurate picture of: - the ethnicity of staff against each AfC pay band - morale, job satisfaction and bullying and harassment of staff. - is the ethnicity of staff representative of the population that the Trust serves. To consider ways to increase ethnicity if there are gaps. | Operational Delivery Group |  | CRH & UHDB Workforce leads and EDI leads | Ongoing | Trust workforce and EDI leads to present annual data to ODG on: - WRES indicators 1 to 8 for midwives and nurses in local maternity and neonatal services - Staff survey results with emphasis on the experience by ethnicity Trusts to present reports and action plans to ODG twice yearly on improving the work experience by ethnic minority staff | Not yet delivered | On track | In collaboration with the WRES team, NHS England's CMiDO team is developing a national report for maternity workforce to improve equity, diversity and inclusion in workforce experience and related reduction in avoidable health inequalities. The report will include a review of current research, establishing a national dashboard, recommendations for improvement in career progression, workforce retention, health and wellbeing, and the future of leadership development. CRH - Equality culture survey gathering staff opinion. HR led culture review within maternity care services. UHDB - IPiP culture survey includes equity questions
4 | Collaborative working with Higher Education Institutions | Establish networks with training sites that deliver qualifications in nursing and midwifery to encourage and support applicants from BAME backgrounds | Linking with course tutorsand student enrolment in HEIs to explore ways of supporting the application process for applicants from BAME backgrounds | Workforce, digital and data planning |  | CRH & UHDB Midwifery Practice Development Teams | Ongoing | Trust midwifery practice development teams to provide a report on the percentage of matenity and neonatal students from ethnic minority background to be presented to ODG annually | Not yet delivered | Not started
5 | Inclusive leadership | Ensure that team leaders and service managers are familiar with how to adapt the workplace to meet the diverse needs of staff | Provide training sessions | Workforce, digital and data planning |  | CRH & UHDB Midwifery Practice Development Teams |  | Trust midwifery practice development teams to provide a report on the training provided and percentage of maternity and neonatal staff that attended | Not yet delivered | Not started | CRH - Flexible working policies in place. Trust working on disability policy. Menopause policy in place. Staff networks to support Race and Disability. UHDB - Trust run a two day Learning & Management study day which is held for all staff in senior positions, open to Band 6 and above, covers recruiting through an inclusive process, person centered policies, all leaders supported to develop an inclusive culture. Diversity champions have also been introduced.

## Enablers
Enablers
LMNS are asked to create the conditions to help achieve equity by considering the factors that will support high quality clinical care and work with system partners and the VCSE sector to address the social determinants of health
Intervention | Action | Detail | Milestone | Mapped to LMNS workstream | Patient insight Patient experience | Responsible owner/s | Timescales | Metrics for success Specific Data Sources | Delivery status | Progress status | Update May 23
1 | Establish community hubs in the areas with the greatest maternal and perinatal health needs | Explore how MCoC teams can link to Family Hubs and Children's Centres to support women, birthing people and babies | Map out maternity care being delivered in community hubs against those areas of high deprivation | Operational Delivery Group |  | CoC leads Maternity services | 2024-03-01 | Report to ODG twice yearly to evidence community hubs in areas of highest deprivation and of working with women and families to improve services | Not yet delivered | Not started
2 | Work with system partners and the VCSE sector to address the social determinants of health | Ensure that pregnant women are signposted to financial inclusion and cost of living support if required. | Understand how pregnant people who are struggling financially are supported by maternity services utlising every contact counts principles | Equity and Equality Core Group |  | Maternity services | 2023-12-01 | List the options for financial inclusion and support services, obtain feedback from stakeholders on awareness of and referral to services presenting to Equity and Equality Group and documented in minutes | Delivered, not yet evidenced | On track | Cost of living support information available at: County: https://www.derbyshire.gov.uk/community/cost-of-living/cost-of-living.aspx City: https://www.communityactionderby.org.uk/crisis-support/help-with-the-cost-of-living
|  | Local guidance for food banks on the emergency provision of infant milk | Develop and agree local pathway for the provision of emergency formula milk in line with the updated UNICEF guidance | Maternal Health and Wellbeing |  | Public Health | 2024-03-01 | Demonstrate that a pathway is in place that ensures emergency formula milk is available to those that require it and present numbers accessing by demographic group to Health and Wellbeing Group and documented in the minutes | Not yet delivered | On track | Pathway is in development by the Infant Feeding Steering Group in line with UNICEF guidance. PH are leading T&F and have identified budget to support the pathway for the first year.
|  | To seek, and listen to the voices of populations more likely to experience poorer outcomes, and utilise opportunities working with VCS organisations for meaningful co-production | To identify opportunities for coproduction by sharing information on projects across the LMNS and introduce service users to organisations to work together Recognise that staff also form part of the community and population and may wish to contribute to service development as the voice of a parent | Equity and Equality Core Group |  | LMNS | Ongoing | Evidence that inclusion of population experience is included in all decision making within the LMNS as documented in minutes and action logs. | Not yet delivered | On track
3 | Services listen to and work with women of all backgrounds to improve access, plan and deliver personalised care. | The Derbyshire Maternal and Neonatal Voices (DMNV) ensures that all groups are heard to generate ideas and new actions for meaningful co-production of maternity and neonatal services | Annual plan developed | Equity and Equality Core Group |  | DMNV | Ongoing | Evidence that maternity service development is co-produced to meets the needs of the local population through DMNV reports | Not yet delivered | On track

## Sheet7
Perinatal Quality and Safety Group
Perinatal Safety Forum
Operational Delivery Group
Neonatal
Choice and Personalisation
Workforce, digital and data planning
Maternal Health and Wellbeing
Equity and Equality Core Group
Delivery status | Description
Not yet delivered | Action is not yet in place, there are outstanding tasks to deliver
Delivered, not yet evidenced | Action is in place with all tasks completed, but has not yet been assured/evidenced as delivering the required improvments
Evidenced and assured | Action is in place with assurance/evidence that the action has been / continued to be addressed
Progress status | Description
Not started | Work on tasks required to deliver this action hs not yet started
Off track | Achievement of the action has missed the scheduled deadline. An exception report much be created to explain why, along with mitigating actions where possible
At risk | There is risk that achievement of the action may miss the scheduled deadline or quality tolerances, but the owner judges that this can be remedied without needing to escalate. An exception report must be created to explain why exception may occur, along with mitigating actions, where possible
On track | Work to deliver this action is underwaqy and expected to meet deadline and quality tolerances
Complete | The work to deliver this action has been completd and there is assurance/evidence that the action is being delivered and sustained