## Slide 1
MHLDA IQT Programme Highlight Report
Derbyshire
Lead: Joe Thompson | Area of Focus: Culture of Care | Guiding Policy: Strength-based shared approach to flexible care provision, risk management and oversight.
Updates and achievements: |  | Issues/ Risks:
All wards have fortnightly coaching sessions booked in with CoC Coach 30 change ideas have been identified by the wards taking part in the programme and have been imported onto the culture of care national dashboard. Derbyshire healthcare are one of only three Trusts that have submitted benchmarking data and have a process to sustain this and provide monthly data on number of incidents of: Restrictive practice (restraint, seclusion and rapid tranquilisation),Sexual harm, The number of days since the last incident of absent without leave (AWOL),The percentage of shifts filled by bank and agency staff. Organisational level support sessions to be booked in for November by end of June 2025. Executive coaching sessions in place. |  | Medical engagement required for successful implementation of projects. Capacity of ward staff and Matrons to undertake change ideas impacted by making room for dignity programme and recent move to new hospital environment. Limited engagement with patient and carer surveys- being supported by speech and language therapy team. Peer Support Worker Recruitment still outstanding.
 |  | Issues/ Risks and Next Steps:
 |  | Book organisational level support sessions for November. Executive coaching session to take place. Ward teams to continue with fortnightly coaching sessions- Team Leads CoC steering group (collaborative forum) to continue monthly and identify any barriers and receive update from Matrons on individual team progress and will be widened to include expert by experience members. Feedback from patients on wards undertaking programme to be prioritised following change of ward names- Ward Leads. Peer support worker role to be put forward to vacancy control panel- Matrons. Self-assessment against culture of care standards to be explored in August 2025.

## Slide 2
MHLDA IQT Programme Highlight Report
Derbyshire
Lead: Fiona Bretell | Area of Focus: Transforming Care | Guiding Policy: Eliminating the use of long stay detention with no therapeutic benefit.
Updates and achievements: |  | Issues/ Risks and Next Steps:
The JUCD Neurodevelopmental Programme over the last few years has been working to meet the key objectives set out in national priorities such as ‘building the right support’. This included the formation of key workstreams targeting specific areas such as health inequalities, all age diagnosis and care and accommodation. 2024 saw a review of the programme and a refresh, setting new objectives to continue to meet new national standards. The 4 priority areas going forward will focus on: 1. Care Support and Accommodation 2. Preparation for National Changes 3. Finances, Efficiencies and Investments 4. Partnership Working To date a number of actions have been realised in relation to the milestones set out in the strategy: The care and accommodation workstream was established as part of the JUCD ND programme and this has led to a number bespoke services across Derbyshire being built/made available that are enabling long-term discharges (forecasting an estimated 16 discharges this year). The care and accommodation workstream will continue to support the objective of delivering person centred, community based care and treatment. This workstream along with the development of a system wide discharge delivery group The Dynamic Support Process has been reviewed and a standard operating procedure has been developed to ensure consistent service delivery based on national framework, this has been done in conjunction with adult mental health services to ensure the correct gatekeeping processes. Strengthening discharge processes: A new system-wide discharge delivery group has been established to discuss, with key partners, the discharge plans for our long term patients in inpatient beds. |  | Cost improvement requirements, vacancies and changes to leadership operating model across the division poses a risk to progressing the changes within the ND patient assurance team. This is being monitored with the ND divisional governance processes. The trajectory of discharges has some risks attached to this based on delays to builds and delays in transition plans.
 |  | Key Next Steps:
 |  | CTR audit. Continue to develop the Discharge Delivery Group including. oversight and assurance processes being fed into the ND programme.

## Slide 3
MHLDA IQT Programme Highlight Report
Derbyshire
Lead: Libby Runcie | Area of Focus: Quality Assurance Framework | Guiding Policy: Robust governance mechanism in place to ensure inclusive, safe and compassionate care.
Updates and achievements: |  | Issues/ Risks/ Limiting factors/Mitigations:
Self-assessment against culture of care standards to be explored in August 2025. The number of restrictive interventions that have occurred each month our are included as part of the quality chapter which is presented at public board along with an explanation of the data and actions to further reduce restrictive interventions. Since November 2024 a inpatient quality dashboard has been in place and performance against the quality measures within the dashboard are reviewed in a meeting that was held weekly until February 2025 and is now held fortnightly with representation from Clinical, Operational and Corporate staff A Trust wide quality dashboard Including data related to inpatient services compromised of SPC charts with narrative, actions and mitigations is presented at the Trust Quality and Safeguarding committee every two months. All inpatient wards are signed up to the electronic patient survey which allows service users to feedback on their care and treatment via hard copy or QR code and is automatically sent out via text message on discharge. This is in addition to feedback via QR Code related to the culture of care program. All inpatient wards have weekly community meetings to promote engagement and feedback from people using inpatient services alongside dedicated carers meetings to inform further improvement to patient experience. |  | Improved engagement with electronic patient survey required to maximise patient feedback A Quality and Performance early warning system is due to be explored in September 2025 work is ongoing to improve engagement with carers

## Slide 4
MHLDA IQT Programme Highlight Report
Derbyshire
Lead: Beckie Priest | Area of Focus: Therapeutic Environment and Inpatients | Guiding Policy: Provision of reasonable adjustments for those who need them.
Updates and achievements: |  | Issues/Risks:
The two main new hospitals have now been successfully opened and are operating as normal. The next part of the process is to open and repatriate patients to the PICU and Audrey house. Whilst this occurs the refurbishment of Radbourne unit will recommence. The final evaluation of the new hospitals has been produced for NHSE and has also been disseminated more widely. Work continues to develop in relation to the new model of care and culture of care, these are ongoing two year programs. The new environments have been completed for Bluebell ward and both hospitals. These environments have been well received by staff, carers and patients. The design of the building enables delivery of therapeutic activity from the moment a person is admitted. Exercise equipment on the wards enables physical activity to be a part of recovery. Outside spaces, that are directly accessible from the wards themselves, allows access to the outdoors. A trauma informed design allows for peaceful spaces aimed at supporting recovery. Privacy and dignity is maintained in single room ensuites. Additional ‘high car’ rooms allow for care of people with physical healthcare needs, bariatric patients and additional facilities for people with a dual diagnosis of neurodiversity or autism enable more people to be cared for in environments that suit their needs within Derbyshire. This reduces the needs for specialist beds outside of area. The immediacy of activities that supports recovery at the point of admission reduces recovery time and consequently time in hospital. A recent CQC assessment in older adults highlighted the benefits of the therapeutic environment on quality of care and patient experience. |  | There was a delay in some sensory equipment for the sensory rooms. There was a delay in building control for Audrey house. There was a delay in environmental door security requirements for PICU.
 |  | Key Next Steps:
 |  | Opening sensory rooms on every ward. Agreeing physical healthcare activity plan for increased offer engagement and delivery including a launch event later in the year ‘lets get moving’. Opening of Kingfisher (PICU) and Audrey house high dependency ward. Recommencement of refurbishment activity in Radbourne unit.

## Slide 5
MHLDA IQT Programme Highlight Report
Derbyshire
Lead: Lee Doyle | Area of Focus: Living Well and Community | Guiding Policy:. Continue to improve community services.
Updates and achievements: |  | Issues/ Risks:
Mental Health services that are available in the community to support people with mental ill health are changing and improving. In alignment with the Community Mental Health Framework, mental health services are transforming to reach a wider cohort of people, including those who have traditionally fallen between the gaps of primary and secondary care, as well as those people with a severe mental illness. Health services, social care and the voluntary, community and social enterprise (VCSE) sector are working in partnership to deliver new integrated ways of working that are modernising community mental health services for adults and older adults, considering the needs of each local area. In Derbyshire, this is called the Living Well Derbyshire programme. In Derby, it is called the Derby Wellbeing programme. Mobilisation of the Living Well sites concluded its final locality in March 2024, at this stage of the mobilisation, all teams are established and receiving referrals from Primary Care and self-re-introduction only. The volume of referrals received has been steadily increasing and significantly high following the Living Well mobilisation, this number will increase again following expansion of pathways in Phase 2 of the transformation. All areas have mobilised Living Well and receive referrals from Primary Care (GP) and social care Embedding feedback into pathway development – Lived Experience Officer role / feedback forms There is a pathway in place for people to move the long term / short term offer and vice versa Through Integrated Patch Leadership, the No. of introductions and discharges, and waiting lists can be monitored |  | Ongoing risk to the delivery of some of the Roadmap and Phase 2 aims due to the current financial restrictions around recruitment and funding. Living well teams are adjusting workloads around capacity available. Practice Lead – current post holder left this position on 30th May 2025. Due to the DHcFT Operating Model consultation underway, this post has not been recruited to and will be reviewed within the restructure. Discussions have been held to mitigate the gap in the short term. Substance Misuse: this element of the programme is currently on hold owing to wider programme financial pressures. It will be revisited following system agreement and confirmation of programme budget at the beginning of Q3 25/26. Risks have been escalated. Contracts – Funding for county and city adult social care resource supporting Living Well/ Derby Wellbeing is currently only confirmed until March 2026. As above, this will be revisited following system agreement and confirmation of programme budget at the beginning of Q3 25/26. Risks have been escalated.
 |  | Next Steps:
 |  | An expansion of each Single Point of Access to receive referrals from wider primary care pathways, social care, mental health services which includes self re-introduction by person (patient) or their carer (within 24 months of accessing the Living Well/Derby Wellbeing service) The development of local networks and community support, which includes voluntary, community or social enterprise (VCSE) community groups and other support within the local community to continue to improve flow through local network agreement Developing pathways with, perinatal, forensic, substance misuse, eating disorders, community rehab team and other specialist services as well as developing a tailored offer for young adults Creating a seamless movement of people accessing long, and short term offers within Living Well

## Slide 6
Three Year Strategic Plan